## Sprint Backlog
Project Title: CST-247 Project Bierer Reeder Release #: 1 Sprint #: 1
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| 1 | As a Site User I need to be able to login to the site with my account | Create Login View | William Bierer | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1
|  |  | Create Login Controller | William Bierer | 3 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Create Error messaging for the login page | Stuart Reeder | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
| 2 | As a Site User I need to be able to create an account for the site | Create Registration View | William Bierer | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1
|  |  | Create Registration Controller | William Bierer | 3 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0
|  |  | Create Error Messaging for the Registration page | Stuart Reeder | 2 | 0 | 0 | 0 | 0
| 3 | As a Website Administration, I want to be able to store all the user information and access it when neccessary | Create a User Model | Stuart Reeder | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Create a Database for the website | Stuart Reeder | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Create a database table that contains user information | Stuart Reeder | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 21 | 18 | 15 | 12 | 9 | 6 | 4 | 2 | 1 | 0 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 21 | 17 | 17 | 13 | 11 | 10 | 7 | 6 | 4 | 2 | 0

## Product Backlog
Project Title:CST-247 Project
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
S2 | Game Board Pages | 1 | As a User | See the gameboard after I log in | I can play minesweeper | 1 | 2018-02-11
S2 | Backend Services for game logic | 2 | As a User | Play Minesweeper | I can play the game | 1 | 2018-02-11
S2 | Update Database | 3 | As an administrator | Have all the user data stored | I can Manage the users | 1 | 2018-02-11
S3 | AJAX Forms/Partial page updates | 1 | As a User | Be able to play the game without refreshing the page every time i click the board | The game plays more fluidly | 2 | 2018-03-11